## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 用户注册 | 作为一个新闻浏览者，我希望能够注册一个账号，以便于收藏我看过的新闻 | Initial Feature | Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 收藏新闻 | 作为一个新闻浏览者，我希望能把我觉得有意思的新闻收藏下来，以便下次再浏览 | Initial Feature | Not Done | 1 | 96 |  |  | 1 | 0
3 | 1 | 1 | user story | 维护收藏列表 | 作为一个新闻浏览者，我希望能够对我的收藏列表进行修改和删除等操作 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 用户登录 | 作为一个新闻浏览者，我希望能在我注册了账号以后能够进行登录使用功能 | Initial Feature | Done | 1 | 93 |  |  | 0.5 | 0
5 | 1 | 1 | user story | 浏览新闻 | 作为一个新闻浏览者，我希望能够在主页看到新闻流 | Initial Feature | Done | 1 | 93 |  |  | 2 | 0
6 | 1 | 1 | user story | 评论功能 | 作为一个新闻浏览者，我喜欢能在我看到的新闻中发表自己的评论 | Initial Feature | Not Done | 0.5 | 90 |  |  | 3 | 0
7 | 1 | 1 | user story | 夜间模式 | 作为一个新闻浏览者，我希望在晚上浏览新闻的时候能够有夜间模式保护眼睛 | Initial Feature | Not Done | 2 | 90 |  |  | 2 | 0
8 | 1 | 1 | user story | 密码更改 | 作为一个新闻浏览者，我希望能够修改我的账号密码 | Initial Feature | Not Done | 3 | 88 |  |  | 3 | 0
9 | 1 | 2 | user story | 快速搜索新闻 | 作为一个新闻浏览者，我希望能够快速搜索我感兴趣的新闻 | Initial Feature | Not Done | 0.5 | 85 |  |  | 1 | 0
10 | 1 | 2 | user story | 用户注销 | 作为一个新闻浏览者，我希望在不使用此APP时能够注销用户 | Initial Feature | Not Done | 2 | 80 |  |  | 2
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information